Project Plan: Gantt Chart

Indicative fourteen week schedule, late June to September 2026. Shaded cells show when each task is active.

| Task | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Phase 1 Literature and setup |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.1 Finalise review, confirm gap |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.2 Acquire CIC IDS 2017 and 2018 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1.3 Deploy OpenCTI and ingest feeds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 2 Data preparation and labelling |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.1 Clean data, handle imbalance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 Define true and false positive labels |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.3 Build baseline feature set A |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 3 Threat intelligence features |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.1 Map attack classes to ATT&CK |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.2 Engineer CTI features |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3.3 Build enriched feature set B |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 4 Model development |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.1 Train and tune Random Forest |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4.2 Train and tune XGBoost |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 5 Evaluation and explainability |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.1 Standard split (core result) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.2 Across time evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.3 Across dataset evaluation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.4 SHAP explainability analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5.5 Significance testing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Phase 6 Writing and submission |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.1 Draft chapters as work proceeds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.2 Supervisor feedback and revision |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.3 Demonstration preparation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6.4 Finalise, proofread and submit |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Figure 1. Gantt chart of the project plan.

Key Milestones

| Milestone | Timing | Meaning |
| --- | --- | --- |
| M1 | End of Week 2 | Environment and data ready |
| M2 | End of Week 4 | Labelled baseline dataset ready |
| M3 | End of Week 6 | Feature sets A and B complete |
| M4 | End of Week 8 | Core models trained |
| M5 | End of Week 9 | Core result obtained, answers RQ2 (minimum viable result) |
| M6 | End of Week 11 | All results complete, answers RQ3 and RQ4 |
| M7 | End of Week 14 | Dissertation submitted |